## MIS Components
Component | Purpose | Core Functionalities | Mapped APIs | Used In | Estimation (Man Days)
LDAP + Token Authentication | Authenticate internal users using LDAP & JWT tokens | - Search LDAP users for identity - Token-based session handling - Secure session storage | POST /api/auth/login GET /api/auth/session | Global | 3
Session Timeout Handler | Maintain session security | - Detect inactivity - Refresh or expire session - Auto logout after threshold | Handled via middleware or NextAuth config | Global | 1
Access Control Wrapper | Restrict route access based on role/permissions | - Check user role - Redirect unauthorized access - Conditionally render components | GET /api/users/me GET /api/roles | Layout, Routing | 2
MainContainer | Layout container for the main app sections | - Provide consistent padding and layout - Responsive behavior - Acts as wrapper for content | N/A | All Pages | 1.5
TopNavBar | Display app name, user info and logout | - App title - Logged-in user info - Logout button - Theme toggler (optional) | GET /api/users/me POST /api/auth/logout | All Pages | 1.5
SideNavBar | Navigation to main app sections | - Link to Users, Reports, Admin - Active tab highlight - Collapsible sections | N/A | All Pages | 2
New User Form | Create a new internal user with full details | - Multi-section form - Validation and submission - Role assignment | POST /api/users/create | Users Page | 1
User Info Sections | Display editable user details | - Render tabs (User, Personal, HR, etc.) - Save updates | GET /api/users/{id} PUT /api/users/{id} | Users Page | 1
File Upload Section | Upload and manage user-related documents | - File input - Document list with preview/download - Metadata storage | POST /api/users/{id}/files GET /api/users/{id}/files | Users Page | 1
Comments Section | Add comments to a user's profile | - Add/edit/delete comments - Timestamp display | GET /api/users/{id}/comments POST /api/comments | Users Page | 1
LDAP Search | Search LDAP directory for user info | - Search by name/email - Show user profile preview - Autofill form with selected data | GET /api/ldap/search | Users Page | 4
Reports List | Display all available downloadable reports | - Fetch report metadata - Display in table/list - Click to download | GET /api/reports | Reports Page | 3
Download Handler | Trigger file download securely | - Handle download on click - Error handling & feedback | GET /api/reports/{report_id}/download | Reports Page | 2
Application Selector | Choose app to manage roles/permissions | - Dropdown of available apps - Load current permissions | GET /api/apps | Admin Page | 2
Role & Permission Grid | Set and modify app-specific roles and permissions | - Matrix view of permissions - Select/unselect checkboxes - Save roles | GET /api/roles?app={id} POST /api/roles/save | Admin Page | 2
Show Hidden Toggle | Toggle visibility of hidden applications | - Switch component to show/hide hidden apps - Updates the permission grid | N/A (local state) | Admin Page | 2
View & Save Buttons | Trigger load or save of role permissions | - Load current state - Save to backend on click | GET /api/roles/view POST /api/roles/save | Admin Page | 1.5
RequestEntitlementPage | Allow users to request new entitlements based on vendor/application and product selection. | - Select sponsor from searchable list - Choose vendor (delivery channel) - Select products (checkbox options) - Submit request (API call) - Display pending requests with filters | GET /api/sponsors GET /api/vendors POST /api/entitlements/request GET /api/entitlements/pending | Request Entitlement | 2.5
PendingRequestsTable | Display all pending entitlement requests with filter and status information. | - Filter by delivery channel, vendor, sponsor, product, user - Show request status and action options - Pagination and search | GET /api/entitlements/pending | Request Entitlement → Pending Requests | 1.5
SearchUserDropdown | Search and select internal users for request actions. | - Debounced search on input - Display results with name & email - Allow selection to drive user-specific actions | GET /api/users/search?q={query} | Request Entitlement → Search User | 1
ApprovalsPage | Display a summary of approvals, and allow managers to approve/reject requests. | - Summary metrics (total, pending, rejected) - List of approval requests - Approve/Reject action buttons | GET /api/approvals POST /api/approvals/{id}/approve POST /api/approvals/{id}/reject | Approvals Section | 2
ActiveEntitlementsList | Show all currently active entitlements. | - Filter by vendor, product, delivery channel - Display user and entitlement details - Remove entitlement request | GET /api/entitlements/active DELETE /api/entitlements/{id} | Active Entitlements Section | 2
EntitlementHistoryPage | View and export historical entitlement requests. | - Filter request history - Export data to Excel file - Paginate and sort records | GET /api/entitlements/history GET /api/entitlements/history/export | History Section | 1.5
Reusable UI & Tech Stack Integration
Component | Purpose | Core Functionalities | Mapped APIs | Used In | Estimation (Man Days)
Form Libraries & Validation | Form handling with React Hook Form/Yup | - Create reusable forms - Add validation rules | N/A | Global | 1
Role-based Access HOC | Wrap components with access logic | - Show/hide based on permissions - Route guards | N/A | Global | 1.5
UI Component Library | Reusable controls and styling | - Define Button, Input, Modal, Select, Loader, etc. | N/A | Global | 2
Global Error Handling | Error boundaries, 404/500 pages | - ErrorFallback component - Catch async API errors | N/A | Global | 1
Environment Configuration | Configure environments via .env | - Dev/stage/prod setups - Toggle flags | N/A | App Config | 0.5
State Mgmt & Routing Patterns
Component | Purpose | Core Functionalities | Mapped APIs | Used In | Estimation (Man Days)
React.js + Redux Setup | Frontend framework and state setup | - Create base structure - Setup Redux slices, middleware - Integrate router | N/A | App Initialization | 2
Spring Boot Setup | Backend application setup | - Create base Spring Boot app - Setup security, dependencies, env config | N/A | Backend Init | 2
Routing & Layout Integration | Define routes, layout shells | - Configure React Router - Integrate MainContainer and layout patterns | N/A | App Init | 1.5
API Service Layer (Axios) | Create reusable API layer | - Interceptor setup - Token handling - Error retry logic | N/A | Global | 1

## State Mgmt & Routing Patterns
Component | Purpose | Core Functionalities | Mapped APIs | Used In | Estimation (Man Days)
React.js + Redux Setup | Frontend framework and state setup | - Create base structure - Setup Redux slices, middleware - Integrate router | N/A | App Initialization | 2
Spring Boot Setup | Backend application setup | - Create base Spring Boot app - Setup security, dependencies, env config | N/A | Backend Init | 2
Routing & Layout Integration | Define routes, layout shells | - Configure React Router - Integrate MainContainer and layout patterns | N/A | App Init | 1.5
API Service Layer (Axios) | Create reusable API layer | - Interceptor setup - Token handling - Error retry logic | N/A | Global | 1