## UI Components
Category | Component | Option 1 (React Description) | Option 1 Effort (Days) | Option 2 (Angular Description) | Option 2 Effort (Days)
Common Modules | App Shell (Navbar, Sidebar, Footer) | Rewrite using React layout | 5 | Minor UI tweaks | 2
Common Modules | Role-aware Routing | React-Router + Context | 3 | Extend route logic | 1
Common Modules | Route Guard | ProtectedRoute wrapper in React | 2 | Reuse Angular Guards | 1
Common Modules | Redux/State | Context/Redux setup | 3 | Use Angular Service | 1
Auth & Session | Login via Okta | Use Okta SDK (React) | 4 | Reuse | 1
Auth & Session | Token & Role Context | Context based handler | 2 | Already exists | 1
Auth & Session | Protected Routes | Wrapper & checks | 2 | Already exists | 1
Entity Management | Internal User List | New Table in React | 5 | Build new in Angular | 5
Entity Management | Add/Edit User | Multi-tab Form React | 6 | Angular reactive form | 6
Entity Management | External Access Form | React form reuse logic | 4 | Reuse | 2
Entity Management | My Requests View | Cards/status in React | 3 | Reuse | 2
Entity Management | Entitlement Grid | React matrix table | 5 | Extend Angular Grid | 3
Admin Tools | Role Matrix | New grid in React | 4 | Reuse or enhance | 2
Admin Tools | Team Mapping | New React UI | 3 | New Angular Module | 3
Admin Tools | Settings Page | React Form + Toggles | 3 | Extend existing | 2
Admin Tools | Certification Manager | React + cert logic | 4 | New Angular form | 4
Admin Tools | Access History Drawer | React right drawer | 3 | Add Angular component | 2
Reports | Access Report | Table + Chart in React | 4 | Angular Table + Chart | 3
Reports | Audit Log Viewer | Paginated filter table | 3 | Extend Angular table | 2
Reports | Entitlement Change Log | React table view | 3 | Add Angular view | 2
Reports | Export | React export plugin | 2 | Use existing plugin | 1
Notifications | Bell/Toasts | React toast + bell | 2 | Already exists | 1
Notifications | Rule Config | React config panel | 3 | Angular Admin Config | 2
Soft Delete | Deactivation Modal | React modal | 2 | Angular Dialog | 1
Soft Delete | Deleted User List | React table | 2 | New Angular view | 1
Soft Delete | Restore/Delete | React buttons/actions | 2 | Add Angular logic | 1
Reusable | SearchBar | React Ant/MUI filter | 2 | Already exists | 1
Reusable | AGGrid Wrapper | React AGGrid table | 2 | Reuse | 1
Reusable | Status Tags | Styled tags React | 1 | Reuse | 1
Reusable | MultiSelect | React select/dropdown | 1 | Reuse | 1
Reusable | Modal Forms | Reusable modal | 2 | Reuse | 1
Reusable | File Upload | React Dropzone/Uppy | 2 | Reuse | 1
Reusable | Quick Actions | React menus | 2 | Reuse | 1
Reusable | Breadcrumbs | React nav trail | 1 | Reuse | 1
Reusable | StepperForm | Custom Stepper | 3 | New in Angular | 3
Reusable | Tab Layout | React tab container | 2 | Reuse | 1

## API Components
Module | API Endpoint | Status | Ownership | Option 1 (React Strategy) | Option 1 Effort (Days) | Option 2 (Angular Strategy) | Option 2 Effort (Days)
Access Requests | GET /api/entitlement/request | Existing | Entitlement | Reuse | 1 | Reuse | 1
Access Requests | POST /api/entitlement/request | Existing | Entitlement | Reuse | 1 | Reuse | 1
Access Requests | POST /api/entitlement/request/upload/{uploadType} | Existing | Entitlement | Reuse | 1 | Reuse | 1
Access Requests | POST /api/entitlement/request/historical-remove | Existing | Entitlement | Reuse | 1 | Reuse | 1
Access Requests | POST /api/entitlement/request/completed | Existing | Entitlement | Reuse | 1 | Reuse | 1
Access Requests | POST /api/entitlement/request/bulk-remove | Existing | Entitlement | Reuse | 1 | Reuse | 1
Approval Workflow | POST /api/entitlement/request/assign-sponsor | Existing | Entitlement | Reuse | 1 | Reuse | 1
Approval Workflow | POST /api/entitlement/request/approve | Existing | Entitlement | Reuse | 1 | Reuse | 1
Approval Workflow | POST /api/entitlement/request/approveMultiple | Existing | Entitlement | Reuse | 1 | Reuse | 1
Request Details | GET /api/entitlement/request/contactEmail | Existing | Entitlement | Reuse | 1 | Reuse | 1
Request Details | GET /api/entitlement/request/view/{requestedByEmail} | Existing | Entitlement | Reuse | 1 | Reuse | 1
Request Details | POST /api/entitlement/request/pending-vendor-update | Existing | Entitlement | Reuse | 1 | Reuse | 1
Entitlements | GET /api/entitlement/history | Existing | Entitlement | Reuse | 1 | Reuse | 1
Entitlements | POST /api/entitlement/active | Existing | Entitlement | Reuse | 1 | Reuse | 1
Entitlements | GET /api/entitlement | Existing | Entitlement | Reuse | 1 | Reuse | 1
Entitlements | GET /api/entitlement/{contactEmail} | Existing | Entitlement | Reuse | 1 | Reuse | 1
Entitlements | GET /api/entitlement/{contactEmail}/{vendorName} | Existing | Entitlement | Reuse | 1 | Reuse | 1
Audit Trail | GET /api/entitlement/request/audit/{entitlementRequestId} | Existing | Entitlement | Reuse | 1 | Reuse | 1
Audit Trail | GET /api/entitlement/fetch/audit/{contactEmail} | Existing | Entitlement | Reuse | 1 | Reuse | 1
User Management | GET /api/mis/users | New | MIS | Build New | 3 | Build | 3
User Management | POST /api/mis/users | New | MIS | Build New | 3 | Build | 3
User Management | PUT /api/mis/users/{id} | New | MIS | Build New | 3 | Build | 3
User Management | DELETE /api/mis/users/{id} | New | MIS | Build New | 3 | Build | 3
HR/Access/Cert | POST /api/mis/user/hr | New | MIS | Build | 2 | Build | 2
HR/Access/Cert | POST /api/mis/user/access | New | MIS | Build | 2 | Build | 2
HR/Access/Cert | POST /api/mis/user/certification | New | MIS | Build | 2 | Build | 2
HR/Access/Cert | POST /api/mis/user/files | New | MIS | Build | 2 | Build | 2
Admin Tools | GET /api/mis/roles/matrix | New | MIS | Build | 2 | Build | 2
Admin Tools | POST /api/mis/roles/matrix | New | MIS | Build | 2 | Build | 2
Reporting | GET /api/mis/reports/certifications | New | MIS | Build | 2 | Build | 2
Reporting | GET /api/mis/reports/audit | New | MIS | Build | 2 | Build | 2
Lookups | GET /api/mis/lookup | New | MIS | Build | 2 | Build | 2